## Open POA&M Items
POAM ID | Controls | Weakness Name | Weakness Description | Weakness Detector Source | Weakness Source Identifier | Asset Identifier | Point of Contact | Resources Required | Overall Remediation Plan | Original Detection Date | Planned Milestones | Milestone Changes | Status Date | Vendor Dependency | Last Vendor Check-in Date | Vendor Dependent Product Name | Original Risk Rating | Adjusted Risk Rating | Risk Adjustment | False Positive | Operational Requirement | Deviation Rationale | Supporting Documents | Comments | Auto-Approve
Unique identifier for each POAM Item | Applicable 800-53 Control(s) | Name of the weakness as provided by the scanner or otherwise summarizing the weakness | Description of the weakness and other information | The scanner name or other source that detected the vulnerability | Vulnerability identifier (Plugin ID) as provided by scanner (plugin ID/None) | Identifier Specified in the Inventory This is a unique string associated with the asset, it could just be IP, or any arbitrary naming scheme This Field should include the complete identifier (no short hand), along with the port and protocol when provided by the scanner. Each Asset should be separated by a new line (Alt+Enter) | Person Responsible for implementing this task | Specify resources needed beyond current resources to mitigate task. | General overview of the remediation plan | Date the weakness was first identified (aka Discovery Date) | Permanent Column List of proposed Milestones, separated with a blank line (Alt+Enter) Any alterations should be made in "Milestone Changes" Milestone Number should be unique to each milestone | Any alterations, status updates, or additions to the milestones. (Milestone Number) [Type of update] [milestone date] : How and why the date changed, or the milestone was altered Create a new Milestone Number for new Milestones | Date POA&M item was last changed or closed | Whether or not this item is vendor dependent. | Date of last vendor check-in, if applicable | Name of the product that is dependent upon the vendor. | Provide the Original Risk Rating from the scanner | Provide the Adjusted Risk Rating as approved by the CIO | Whether there was a Risk Adjustment | Whether this weakness should be considered a False Positive | Whether this weakness should be considered an Operational Requirement | Information about the Deviation | List any supporting documents that are associated with this item (e.g. Deviation Request, Evidence of Remediation, Evidence of Vendor Dependency, etc) | This column is for additional information, not specified in another column | Whether the deviation request was auto-approved or manually approved
Unique Identifier | Control Number | Text | Text | [Nessus, Qualys, Webinspect, Security Assessment Report, etc] | Identifier | Identifier (port/protocol) | Text | Text | Text | Date | (##) xxxx-xx-xx: Milestone Description | (##) New/Update/Complete xxxx-xx-xx : Description of change | Date | Yes, No | Date | Product Name | Low, Moderate, High | Low, Moderate, High, N/A | Yes, No, Pending | Yes, No, Pending | Yes, No, Pending | Deviation Type : Rationale | Document Type : Document Name | Text | Yes, No
RISEN_AC_POAM_1 | AC-2(3).1 | No defined time period for inactive accounts via Policy and Procedures | RISEN does not have a defined time period to disable inactive accounts documented. | RISEN AC SAR 03/06/2022 | 03/06/2022 6:52:00 PM RISEN AC Policy and Procedure documentation review. |  | Kandace Davis | Policies & Procedures writer | Develop, submit for approval, and implement Access Control Protection Policies & Procedures. | 2022-03-06 | (01) 2022.10.04 - Identify resource (02) 2022.11.04 - Develop requirements (03) 2021.12.04 - Submit initial draft of Media Protection policy & procedures (04) 2022.13.04 - Submit final draft of Media Protection policy & procedures |  |  | Yes |  |  | Low | N/A | No | No | Yes
RISEN_AC_POAM_2 | AC-17.3.1 |  | LuxNet has no process to mark media to indicate restrictions | Lux Net SAR 10/19/21 | 9/20/2021 5:23:00 PM Interview with Rose Donald, ISSO. |  | Rose Donald | Process developer | Include process for marking media in Media Protection procedures | 2021-09-20 | (01) 2022.01.06 Complete Media Protection policy & procedures (02) Identify Media requiring markings (03) Determine markings required (04) Identify tools/materials to use for marking (05) Complete markings |  |  | Yes |  |  | High | N/A | No | No | Yes
LuxNet_2021_3 | MP-6(1).5 | No media sanitization process | Luxnet has no process to verify media sanitization and disposal actions | LuxNet SAR 10/19/2021 | 9/19/2021 5:23:00 PM Interview with Rose Donald, ISSO. |  | Rose Donald | Process developer | Develop organizational processes for media sanitization or automated mechanisms supporting and/or implementing media sanitization | 2021-09-20 | (01) 2021.11.11 - Identify resource (02) 2021.11.25 - Develop requirements (03) 2021.12.09 - Submit initial draft of Media sanitization process (04) 2022.01.06 - Submit final draft of Media sanitization process |  |  | Yes |  |  | High | N/A | No | No | Yes
LuxNet_2021_5 | PS-5.a.1 | No Security Policy & Procedures. | LuxNet does not currently have personnel security Policy & Procedures. | LuxNet SAR 10/19/2021 | 9/19/2021 6:25PM Interview with Rose Donald (ISSO) |  | Rose Donald | Policies & Procedures writer | Develop, submit for approval, and implement Personnel Security Policies and Procedures for Lux Net | 2021-09-19 | (01) 2020.11.11 - Identify resource (02) 2020.11.25 - Develop requirements (03) 2020.12.09 - Submit initial Draft (04) 2021.01.06 - Submit final Draft |  |  | Yes |  |  | High | N/A | No | No | Yes
LuxNet_2021_8 | PS-6.c.2.2 | Access agreements not resigned | Users have not resigned LuxNet's Rules of Behavior. | LuxNet SAR 10/19/2021 | 9/14/2021 2:49PM Interview with Rose Donald(ISSO) |  | Rose Donald | Policies & Procedures writer | LuxNet plans to have them done in the next few weeks | 2021-09-18 | (01) 2021.11.30 Update Rules of Behavior (02) 2021.12.14 Develop training to review ROB (03) 2021.12.28 Deliver training and collect signatures |  |  | Yes |  |  | High | N/A | No | No | Yes